## Slide 1: ICONE TDR results
Nicolas Pichoff
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
https://www.icone-neutron.fr/

## Slide 2: ICONE Project main goal
2
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
Deliver a national facility for about ~300 experiments/year
 12 instruments : According to scientific case
 2 neutron sources : High Flux (HF) : ~2 ms@20Hz (4% DC)
 1 proton accelerator : 25 MeV, 80 mA @ 8% of Duty Cycle (DC)
Project requirements (end of 2023) :
 Phase 1 : First neutrons & instruments in 2033 (2034, for users)
 Phase 2 : Full capability in 2037
 TDR 2024-2025  Construction plan consolidation
If GO<2026
If GO<~2032
High Resolution (HR) : ~400 µs@50Hz (2% DC)
Results presented here

## Slide 3: Organisation
3
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
Steering Committee (CEA, CNRS)
SO
A. Desmedt (CNRS)
PMO
T. Vassiliadès (CNRS)
WP3: TMR Sets
F. Ott (CEA)
Neutron production
Scientific Advisory Board
Neutron use
WP4: LINAC
D. Uriot (CEA)
Proton production
WP1: PROJET MANAGEMENT
WP2: INSTRUMENTS
X. Fabrèges (CNRS)
PL
N. Pichoff (CEA)
Resource Committee
Control Committee (CEA, CNRS, MESR)
WP5: INFRASTRUCTURE
A. Ferland (CEA)
Infrastructure hosting
Academic, Industrial and society goals
Project leading (Budget, Schedule, risks…)

## Slide 4: Global view ( 2037)
4
Zone 1
Zone 2
Zone 3
Zone 1
Zone 2
XDTL-7m (25 MeV)
XDTL-5.5m (12 MeV)
RFQ-4.6m (3.6 MeV)
MEBT-2.2m (3.6 MeV)
SRC+LEBT-3.5m (0.75 MeV)
LINAC-31m (40 MeV)
Zone 3
Zone 4
Zone 4
315 cm
XDTL-8m (40 MeV)
350 cm
350 cm
Office area
4321,5 m2
Reception
55 m2
1:500
1 cm = 5 m
1 m2
Zone 1
40 m
Zone 7
Zone 2
41 m
Zone 3
44 m
Zone 4
445m
Zone 5
36 m
Zone 6
31 m
Zone 9
1 m2
Zone 1
30 m
Zone 7
Zone 2
31 m
Zone 3
33 m
Zone 4
29 m
Zone 5
24 m
Zone 6
21 m
Zone 9
Zone 2
Zone 1
Zone 3
Zone 4
1 m2
Zone 5
Zone 5
Zone 5
Zone 5
Zone 2
Zone 1
Zone 3
Zone 4
Zone 5
Zone 5
Zone 5
Zone 5
Technical area
2221 m2
77 m
65 m
- Accelerator p+, 80 mA, 25 MeV @ 8%DC
- 6 instruments HR (<44 m)
- Target 1 : 0.4 ms@50 Hz (2% DC)
- Target 2 : 2.0 ms@20 Hz (4% DC)
- Neutron Peak Brilliance :
~ 5 1011 /s/cm2/sr/Å @ 1 Å et 2.5 Å
~ 1011 /s/cm2/sr/Å @ 5 Å
- 6 instruments HF (<33 m)
- Staff buildings :
- Technical area (~1000 m2)
- Office area (~1500 m2)
26/11/2025 – MLZ/LLB workshop – ICONE TDR results

## Slide 5: Phase 1 ( 2034)
5
Zone 1
Zone 2
Zone 3
Zone 1
Zone 2
XDTL-7m (25 MeV)
XDTL-5.5m (12 MeV)
RFQ-4.6m (3.6 MeV)
MEBT-2.2m (3.6 MeV)
SRC+LEBT-3.5m (0.75 MeV)
LINAC-31m (40 MeV)
Zone 3
Zone 4
Zone 4
315 cm
XDTL-8m (40 MeV)
350 cm
350 cm
55 m2
1:500
1 cm = 5 m
1 m2
Zone 1
40 m
Zone 7
Zone 2
41 m
Zone 3
44 m
Zone 4
445m
Zone 5
36 m
Zone 6
31 m
Zone 9
Zone 2
Zone 1
Zone 3
Zone 4
1 m2
Zone 5
Zone 5
Zone 5
Zone 5
- Accelerator p+, 80 mA, 25 MeV @ 8%DC
- 3 instruments HR (<44 m)
- Target 1 : 0.4 ms@50 Hz (2% DC)
- Target 2 : 2.0 ms@20 Hz (4% DC)
- Neutron Peak Brilliance :
~ 5 1011 /s/cm2/sr/Å @ 1 Å et 2.5 Å
~ 1011 /s/cm2/sr/Å @ 5 Å
- 3 instruments HF (<33 m)
- Staff buildings :
- Technical area (~600 m2)
- Office area (~1500 m2)
Reception
Technical area
2221 m2
26/11/2025 – MLZ/LLB workshop – ICONE TDR results

## Slide 6: Position
6
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
Saclay CEA center

## Slide 7: Artist’s rendering
7
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
Courtesy : X. Fabrèges

## Slide 8: Construction planning
8
RBS - Requirements
WBS - Work
PBS - Product
From need to product…
…
to plan
26/11/2025 – MLZ/LLB workshop – ICONE TDR results

## Slide 9: Scientific case (WP1)
9
 Specifications for expected performances and for instruments
26/11/2025 – MLZ/LLB workshop – ICONE TDR results

## Slide 10: Instruments (WP2)
10
Neutron guide design
Neutron guide transmission
Slits
Choppers
Sample Irradition
Neutron analysis
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
Sample environnement
Neutron detector
Radioprotection
Radioprotection studies
Experiment simulation
(data processing incl.)
TMR Set
Transport
Sample
Detection
Processing
Neutrons
Signal
Preparation
Useful
Neutrons
Efficient
Neutrons
Experimental area
Radiological protections
Maintenance
information
Science

## Slide 11: Target-Moderator-Reflector (WP3)
11
Reflector (not represented here) will be in Be
26/11/2025 – MLZ/LLB workshop – ICONE TDR results

## Slide 12: Target-Moderator-Reflector (WP3)
12
Target support prototype:
Mechanical tests and
Performances: Peak brightness (cold) between ILL and PSI
Radio-protection: monolithe + bunker
Dose rate : 1012 µSv/h  <0.5 µSv/h
< 0.5 µSv/h
Protons
Neutrons and gammas
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
105
2 103
25
8
Dose rate [µSv/h]

## Slide 13: Linac (WP4)
13
Qpole Proto: built, tests in 2026
Cavity Proto: built, tests in 2026
Design 3D:
RFQ
MEBT
LEBT
26/11/2025 – MLZ/LLB workshop – ICONE TDR results

## Slide 14: Infrastructure (WP5)
14
1
2
3
4
5
6
7
RF hall
8
9
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
Technical area
Office area

## Slide 15: Schedule
15
26/11/2025 – MLZ/LLB workshop – ICONE TDR results

## Slide 16: Conclusion
16
26/11/2025 – MLZ/LLB workshop – ICONE TDR results
Most elements are now designed.
We are ready to start the construction of elements on project critical path :
- RFQ.
- Infrastructure.
Some optimizations and engineering details of non-time-critical elements still have to be completed.
Budget situation is not yet fully stabilized.